## DetroitEntrepreneur
Member: Nicolas
Date | Group Member | Task | Planned hours | Actual hours | Completed?
Week 1
2014-02-11 | Nick | Meet with client | 0.5 | 0.5 | yes
2014-02-12 |  | Establish group communication | 1 | 1 | yes
2014-02-16 |  | Create statement of work draft | 2 | 2 | yes
Week 2
2014-02-18 | Nick | Team meeting | 2 | 2 | yes
Throughout week |  | Email client | 0.5 | 0.5 | yes
2014-02-23 |  | Finish SOW | 2 | 2 | yes
2014-02-23 |  | Evaluations metrix | 0.5 | 0.5 | yes
Week 3
2014-02-24 | Nick | Team meeting | 1 | 1 | yes
|  | Review high level designs | 1 | 1 | yes
Week 4
2014-03-10 | Nick | Develop task breakdown | 1.5 | 2 | yes
2014-03-10 |  | Develop network diagram | 1.5 | 1.5 | yes
2014-03-16 |  | Develop Gantt chart | 1 | 1 | yes
Week 5
2014-03-18 |  | Team meeting | 0.5 | 0.5 | yes
2014-03-23 |  | Update Gantt chart | 1 | 1 | yes
2014-03-23 |  | Update timesheets | 1 | 1.5 | yes
2014-03-21 |  | Communicate with client on layout/design | 2 | 2 | yes
2014-03-21 |  | Establish Wordpress requirements with client | 1 | 1 | yes
Week 6
2014-03-25 |  | Meeting | 0.5
|  | Help team code | 5
Totals |  |  | 25.5 | 21
Member: Zach
Date | Group Member | Task | Planned hours | Actual hours | Completed?
Week 1
2014-02-11 | James | Meet with client | 0.5 | 0.5 | yes
2014-02-16 |  | Develop project deliverables | 0.5 | 0.5 | yes
Week 2
2014-02-18 | Zach | Team meeting | 2 | 2 | yes
Throughout week |  | Brainstorm/research layout | 2 | 2 | yes
Throughout week |  | Make sketches of layout | 1 | 1 | yes
Week 3
2014-02-24 | Zach | Team meeting | 1 | 1 | yes
2014-02-25 |  | Begin prototyping | 2 | 2 | yes
Week 4
2014-03-10 | Zach | Code website | 1.5 | 1.5 | yes
2014-03-14 |  | Code website | 1.5 | 1.5 | yes
Week 5
2014-03-18 |  | Team meeting | 0.5 | 0.5 | yes
2014-03-20 |  | Find possible Wordpress themes | 2 | 2 | yes
|  | Code website | 5 | 5 | no
Week 6
2014-03-25 |  | Meeting | 0.5
|  | Code website | 10
Totals |  |  | 30 | 19.5
Member: James
Date | Group Member | Task | Planned hours | Actual hours | Completed?
Week 1
2014-02-11 | James | Meet with client | 0.5 | 0.5 | yes
2014-02-16 |  | Develop project deliverables | 0.5 | 0.5 | yes
Week 2
2014-02-18 | James | Team meeting | 2 | 2 | yes
Throughout week |  | Research frameworks | 2 | 2 | yes
Week 3
2014-02-24 | James | Team meeting | 1 | 1 | yes
2014-02-25 |  | Develop framework plan | 2 | 2 | yes
Week 4
2014-03-10 | James | Install framework | 1 | 1 | yes
2014-03-13 |  | Code website | 1 | 1 | yes
2014-03-15 |  | Code website | 1 | 1 | yes
Week 5
2014-03-18 |  | Team meeting | 0.5 | 0 | no
|  | Code website | 5 | 5 | no
Week 6
2014-03-25 |  | Meeting | 0.5
|  | Code website | 10
Totals |  |  | 27 | 16
Member: Alicia
Date | Group Member | Task | Planned hours | Actual hours | Completed?
Week 1
2014-02-11 | Alicia | Meet with client | 0.5 | 0.5 | yes
2014-02-16 |  | Develop project deliverables | 0.5 | 0.5 | yes
Week 2
2014-02-18 | Alicia | Team meeting | 2 | 2 | yes
Throughout week |  | Develop color scheme | 2 | 2 | yes
Throughout week |  | Develop font scheme | 1 | 1 | yes
Week 3
2014-02-24 | Alicia | Team meeting | 1 | 1 | yes
2014-02-25 |  | Produce color swatches | 1 | 1 | yes
Week 4
2014-03-13 | Alicia | Work on CSS | 1.5 | 1.5 | yes
2014-03-15 |  | Work on CSS | 1.5 | 1.5 | yes
Week 5
2014-03-18 |  | Team meeting | 0.5 | 0 | no
|  | Work on stylesheets | 5
Week 6
2014-03-25 |  | Meeting | 0.5
|  | Work on stylesheets | 10
Totals |  |  | 27 | 11
Team Totals |  |  | 109.5 | 67.5